## Guidance
ICD-10 Transition Impact Analysis Guidelines
Goal
To identify, evaluate and prioritize risks to high-risk operating systems, and how to monitor and mitigate them. First, facilitate group discussion about risks and risk mitigation; then ask group to come up with specific numbers for the bolded questions.
Activity Purpose
To help PROGRAMS better manage their projects by taking a proactive approach to risk/issue management. This is not just about completing a document. a) It is important to consider risks/issues up front and how their program will be impacted b) It is important to update the log as risks are removed or realized on an ongoing basis.
Directions
Use the following guide/questions to help you identify all of the ways in which your program currently interacts with ICD-9-CM codes. A description of this “as is” state will help to identify potential risks and impacts to complete the risk log and will help you identify the appropriate people from your team who need to be part of the discussion.
Questions
From a SYSTEM perspective, how are you currently using/interacting with ICD-9-CM codes? a) How does your system work? b) What is the first point where the code is touched? i) Data coming in? ii) Is it the pipeline iii) The mechanism where the data are parsed? iv) Is it a data repository v) Does it have to do with sending, receiving, the structure with receiving, or when it gets here c) Based on the described current state, what are the SYSTEM risks in transitioning to ICD-10 code sets?
From a PEOPLE perspective, how you are using/interacting with ICD-9 codes? a) How are your users interacting with ICD-9 codes? b) How are your implementers interacting with ICD-9 codes c) Based on the described current state, what are the risks to PEOPLE in transitioning to ICD-10 code sets? i) Users- will they get the data they need and have what is needed for the new code sets? ii) Implementers- do you have enough people to do what is necessary to prepare for the transition?
What PROCESSES do you have that support ICD-9 work? a) Examples of processes that you might have in place with your program that support ICD-10 work include (but not limited to): i) Data Collection ii) Data Quality Assurance iii) Data Analysis iv) Reporting and data visualization v) Claims processing vi) Reimbursement vii) Claims submission viii) Publications ix) Data interpretation x) Other b) Based on the described current state, what are your PROCESS risks in transitioning to ICD-10 code sets?
Risk Mitigation and Impact
For each risk:
a) Describe potential mitigation strategies i) What can you do to mitigate/prevent that risk from happening?
b) What is the likelihood of the risk occuring i) 1- minimal probability ii) 2- equal risk of occurring or not iii) 3- extreme probability- more than 50/50
c) If the risk occurs, how severe of an effect will it have on business outcomes? i) 1- minor effect; minimal or no effort to address; outcomes unaffected ii) 2- some effect; short term workarounds may be needed iii) 3- extreme effect; require extra resources to address; definite negative effects on outcomes iv) 4- a primary objective will not be accomplished
d) What might trigger/cause this risk to occur?
e) In the transition stage, what dollar impact is expected if the risk were to occur?
f) In the transition stage, what schedule impact is expected if the risk were to occur?
g) In the transition stage, what is your overall assessment of impact/effort to address the risk if it were to occur? i) 1- none ii) 2- minimal iii) 3- some iv) 4- significant
h) In a steady state post-transition, what dollar impact is expected if the risk were to occur?
i) In a steady state post-transition, what schedule impact is expected if the risk were to occur?
j) In a steady state post-transition, what is your overall assessment of the impact/effort required to address the risk if it were to occur? i) 1- none ii) 2- minimal iii) 3- some iv) 4- significant
k) Describe potential contingency plans i) What could your contingency or backup plans be if the risk does occur?
Additional program areas that might be at risk as a result of the transition: a) Budget b) Security c) Technical Obsolescence d) Feasibility e) Reliability of Systems

## Risk Assessent Template
ICD-10 Impact Assessment
Summary
Process or System Name
Description
Contact completing risk assessment
Process/System Owner
Stakeholder(s)
Summary of ICD-10 Usage
Improvement Opportunities
General Notes
Stakeholders
| Internal Stakeholders: | External Stakeholders:
Risks
| Risk Description |  | Risk Score |  |  |  | Work Effort to Mitigate Risk | [6 empty] | Total Impact
# | Risk Description | Risk Strategy & Action Steps ("Mitigation Strategy") | Likelihood of Risk Occurring (L) [Enter 1, 2, or 3] | Severity of Risk if it Occurs (S) [Enter 1, 2, 3, or 10] | Risk (R) = L*S Computed | Trigger Description (Optional) | Transition Effort In Dollars | Transition Effort In Days | Transition Effort Overall Assessment(TrE) [Enter 0, 1, 2, or 3] | Steady State Effort In Dollars | Steady State Effort In Days | Steady State Effort Overall Assessment (SSE) [Enter 0, 1, 2, or 3] | Work Effort (WE) = TrE + SSE Computed | Impact (I) Score = WE+R Computed | Contingency Plan (Optional) | Risk and Work Owner | Notes | Description of the Impact (calculated) | Transition Effort (TrE) Description | Steady State Effort (SSE) Description | Likelihood of Risk | Severity of Risk
Sample | Providers may not be prepared for the ICD-10 transition. If providers code claims incorrectly, then there may be an increase in rejected and resubmitted claims potentially increasing beneficiary and provider inquiries and appeals | Educate providers on the ICD-10 transition | 2 | 3 | 6 |  | $40,000 (cost of training providers) | 30 days (time required to train providers) | 3 |  |  | 0 | 3 | 9 |  |  |  | The function will be somewhat affected if the risks occurs. If the risk occurs, the functional area will have more difficulty preventing the risk from affecting business outcomes. The required corrections and workarounds will incur some incremental costs for the functional area. | The risk will require no activity to address. | The risk will likely require a significant expenditure of resources (e.g. Federal FTEs, contractor FTEs, and internal and external communications) to address. | Minimal probability of taking place | If the risk occurs, it will have some affect on CMS business outcomes. If the risk occurs, CMS can use short term workarounds, but there would be the possibility of affecting the effectiveness or efficiency of the area.
|  |  | 0 | 0 | 0 |  |  |  | 0 |  |  | 0 | 0 | 0 |  |  |  | The function will be minimally affected if the risk occurs. If the risk occurs, the functional area will be able to implement workarounds to prevent the risk from affecting business outcomes. The workarounds will have no or minimal incremental costs. | The risk will require no activity to address. | The risk will likely require a significant expenditure of resources (e.g. Federal FTEs, contractor FTEs, and internal and external communications) to address. | Minimal probability of taking place | If the risk occurs, it will have some affect on CMS business outcomes. If the risk occurs, CMS can use short term workarounds, but there would be the possibility of affecting the effectiveness or efficiency of the area.
|  |  | 0 | 0 | 0 |  |  |  | 0 |  |  | 0 | 0 | 0 |  |  |  | The function will be minimally affected if the risk occurs. If the risk occurs, the functional area will be able to implement workarounds to prevent the risk from affecting business outcomes. The workarounds will have no or minimal incremental costs. | The risk will require no activity to address. | The risk will likely require a significant expenditure of resources (e.g. Federal FTEs, contractor FTEs, and internal and external communications) to address. | Minimal probability of taking place | If the risk occurs, it will have some affect on CMS business outcomes. If the risk occurs, CMS can use short term workarounds, but there would be the possibility of affecting the effectiveness or efficiency of the area.
|  |  | 0 | 0 | 0 |  |  |  | 0 |  |  | 0 | 0 | 0 |  |  |  | The function will be minimally affected if the risk occurs. If the risk occurs, the functional area will be able to implement workarounds to prevent the risk from affecting business outcomes. The workarounds will have no or minimal incremental costs. | The risk will require no activity to address. | The risk will likely require a significant expenditure of resources (e.g. Federal FTEs, contractor FTEs, and internal and external communications) to address. | Minimal probability of taking place | If the risk occurs, it will have some affect on CMS business outcomes. If the risk occurs, CMS can use short term workarounds, but there would be the possibility of affecting the effectiveness or efficiency of the area.
|  |  | 0 | 0 | 0 |  |  |  | 0 |  |  | 0 | 0 | 0 |  |  |  | The function will be minimally affected if the risk occurs. If the risk occurs, the functional area will be able to implement workarounds to prevent the risk from affecting business outcomes. The workarounds will have no or minimal incremental costs. | The risk will require no activity to address. | The risk will likely require a significant expenditure of resources (e.g. Federal FTEs, contractor FTEs, and internal and external communications) to address. | Minimal probability of taking place | If the risk occurs, it will have some affect on CMS business outcomes. If the risk occurs, CMS can use short term workarounds, but there would be the possibility of affecting the effectiveness or efficiency of the area.
|  |  | 0 | 0 | 0 |  |  |  | 0 |  |  | 0 | 0 | 0 |  |  |  | The function will be minimally affected if the risk occurs. If the risk occurs, the functional area will be able to implement workarounds to prevent the risk from affecting business outcomes. The workarounds will have no or minimal incremental costs. | The risk will require no activity to address. | The risk will likely require a significant expenditure of resources (e.g. Federal FTEs, contractor FTEs, and internal and external communications) to address. | Minimal probability of taking place | If the risk occurs, it will have some affect on CMS business outcomes. If the risk occurs, CMS can use short term workarounds, but there would be the possibility of affecting the effectiveness or efficiency of the area.
|  |  | 0 | 0 | 0 |  |  |  | 0 |  |  | 0 | 0 | 0 |  |  |  | The function will be minimally affected if the risk occurs. If the risk occurs, the functional area will be able to implement workarounds to prevent the risk from affecting business outcomes. The workarounds will have no or minimal incremental costs. | The risk will require no activity to address. | The risk will likely require a significant expenditure of resources (e.g. Federal FTEs, contractor FTEs, and internal and external communications) to address. | Minimal probability of taking place | If the risk occurs, it will have some affect on CMS business outcomes. If the risk occurs, CMS can use short term workarounds, but there would be the possibility of affecting the effectiveness or efficiency of the area.
|  |  | 0 | 0 | 0 |  |  |  | 0 |  |  | 0 | 0 | 0 |  |  |  | The function will be minimally affected if the risk occurs. If the risk occurs, the functional area will be able to implement workarounds to prevent the risk from affecting business outcomes. The workarounds will have no or minimal incremental costs. | The risk will require no activity to address. | The risk will likely require a significant expenditure of resources (e.g. Federal FTEs, contractor FTEs, and internal and external communications) to address. | Minimal probability of taking place | If the risk occurs, it will have some affect on CMS business outcomes. If the risk occurs, CMS can use short term workarounds, but there would be the possibility of affecting the effectiveness or efficiency of the area.
|  |  | 0 | 0 | 0 |  |  |  | 0 |  |  | 0 | 0 | 0 |  |  |  | The function will be minimally affected if the risk occurs. If the risk occurs, the functional area will be able to implement workarounds to prevent the risk from affecting business outcomes. The workarounds will have no or minimal incremental costs. | The risk will require no activity to address. | The risk will likely require a significant expenditure of resources (e.g. Federal FTEs, contractor FTEs, and internal and external communications) to address. | Minimal probability of taking place | If the risk occurs, it will have some affect on CMS business outcomes. If the risk occurs, CMS can use short term workarounds, but there would be the possibility of affecting the effectiveness or efficiency of the area.
|  |  | 0 | 0 | 0 |  |  |  | 0 |  |  | 0 | 0 | 0 |  |  |  | The function will be minimally affected if the risk occurs. If the risk occurs, the functional area will be able to implement workarounds to prevent the risk from affecting business outcomes. The workarounds will have no or minimal incremental costs. | The risk will require no activity to address. | The risk will likely require a significant expenditure of resources (e.g. Federal FTEs, contractor FTEs, and internal and external communications) to address. | Minimal probability of taking place | If the risk occurs, it will have some affect on CMS business outcomes. If the risk occurs, CMS can use short term workarounds, but there would be the possibility of affecting the effectiveness or efficiency of the area.
|  |  | 0 | 0 | 0 |  |  |  | 0 |  |  | 0 | 0 | 0 |  |  |  | The function will be minimally affected if the risk occurs. If the risk occurs, the functional area will be able to implement workarounds to prevent the risk from affecting business outcomes. The workarounds will have no or minimal incremental costs. | The risk will require no activity to address. | The risk will likely require a significant expenditure of resources (e.g. Federal FTEs, contractor FTEs, and internal and external communications) to address. | Minimal probability of taking place | If the risk occurs, it will have some affect on CMS business outcomes. If the risk occurs, CMS can use short term workarounds, but there would be the possibility of affecting the effectiveness or efficiency of the area.
|  |  | 0 | 0 | 0 |  |  |  | 0 |  |  | 0 | 0 | 0 |  |  |  | The function will be minimally affected if the risk occurs. If the risk occurs, the functional area will be able to implement workarounds to prevent the risk from affecting business outcomes. The workarounds will have no or minimal incremental costs. | The risk will require no activity to address. | The risk will likely require a significant expenditure of resources (e.g. Federal FTEs, contractor FTEs, and internal and external communications) to address. | Minimal probability of taking place | If the risk occurs, it will have some affect on CMS business outcomes. If the risk occurs, CMS can use short term workarounds, but there would be the possibility of affecting the effectiveness or efficiency of the area.
|  |  | 0 | 0 | 0 |  |  |  | 0 |  |  | 0 | 0 | 0 |  |  |  | The function will be minimally affected if the risk occurs. If the risk occurs, the functional area will be able to implement workarounds to prevent the risk from affecting business outcomes. The workarounds will have no or minimal incremental costs. | The risk will require no activity to address. | The risk will likely require a significant expenditure of resources (e.g. Federal FTEs, contractor FTEs, and internal and external communications) to address. | Minimal probability of taking place | If the risk occurs, it will have some affect on CMS business outcomes. If the risk occurs, CMS can use short term workarounds, but there would be the possibility of affecting the effectiveness or efficiency of the area.
|  |  | 0 | 0 | 0 |  |  |  | 0 |  |  | 0 | 0 | 0 |  |  |  | The function will be minimally affected if the risk occurs. If the risk occurs, the functional area will be able to implement workarounds to prevent the risk from affecting business outcomes. The workarounds will have no or minimal incremental costs. | The risk will require no activity to address. | The risk will likely require a significant expenditure of resources (e.g. Federal FTEs, contractor FTEs, and internal and external communications) to address. | Minimal probability of taking place | If the risk occurs, it will have some affect on CMS business outcomes. If the risk occurs, CMS can use short term workarounds, but there would be the possibility of affecting the effectiveness or efficiency of the area.

## Definitions
Likelihood of Risk
Description | Value | Level
Minimal probability of taking place | 1 | Low
Equal probability of occurring or not taking place | 2 | Moderate
Extreme probability of taking place | 3 | High
Severity of Risk
Description | Value | Level
If the risk occurs, it will have a minor affect on the program's business outcomes and will require minimal or no effort to address. If the risk occurs, CMS can use workarounds to continue business processes and systems without affecting outcomes. | 1 | Low
If the risk occurs, it will have some affect on the program's business outcomes. If the risk occurs, CMS can use short term workarounds, but there would be the possibility of affecting the effectiveness or efficiency of the area. | 2 | Moderate
If the risk occurs, it will have an extreme affect on the program's business outcomes and require more expenditure of resources to address. If the risk occurs, using short term workarounds could not prevent negative affects to outcomes. | 3 | High
If the risk occurs, the effect will derail operations and the program will not be able to accomplish one or more primary objectives. The incident will tarnish the agency’s reputation and temporary fixes will not be feasible to mitigate the risks. | 10 | Catastrophic
Work Effort Scoring for Transition and Steady State Phases
Transition: Level of effort to proactively address/mitigate risks in preparation for ICD-10 transition
Steady State: Level of effort to proactively address/mitigate risks in preparation for ICD-10 transition
Effort in Dollars and Days | Value
Enter the number of days (schedule impact) to address the risk if it occurs and becomes an issue | any
Enter the dollars (budget impact) to address the risk if it occurs and becomes an issue | any
Overall Assessment Description | Value | Level
The risk will require no activity to address. | 0 | None
The risk will likely require a minimal expenditure of resources (e.g. Federal FTEs, contractor FTEs, internal/external communications) to address in preparation for ICD-10 transition. | 1 | Low
The risk will likely require some expenditure of resources (e.g. Federal FTEs, contractor FTEs, and internal and external communications) to address in preparation for ICD-10 transition. | 2 | Moderate
The risk will likely require a significant expenditure of resources (e.g. Federal FTEs, contractor FTEs, and internal and external communications) to address in preparation for ICD-10 transition. | 3 | High
Impact Classification Per Risk
Description | Impact Score Range | Impact Level
The function will be minimally affected if the risk occurs. If the risk occurs, the functional area will be able to implement workarounds to prevent the risk from affecting business outcomes. The workarounds will have no or minimal incremental costs. | 1-5 | Low
The function will be somewhat affected if the risks occurs. If the risk occurs, the functional area will have more difficulty preventing the risk from affecting business outcomes. The required corrections and workarounds will incur some incremental costs for the functional area. | 6-12 | Moderate
The function will be significantly affected if the risk occurs. If the risk occurs, the functional area will not be able to prevent the risk from affecting business outcomes. The required corrections and workarounds will require substantial incremental costs for the functional area and/or do not exist to mitigate the risks. | 13-36 | High