## R11.2 Issues Backlog
Id | Component | Module | Title | Priority | Status | Date Opened | Description | CMS Impact | Release Date
10013 | Dialysis | Analysis and Reporting | Rate Table in Vascular Access Infection report is not Displaying correct number of months for Facility and Groups | 1-Urgent | A&R-In-Progress | 2021-11-17 08:59 | The report is not displaying the correct number of months reported for a facility or group. When run for a group for a specific time period, the aggregate counts in the top and bottom of the report are not displaying the correct total number of months. The report appears to be excluding some months. | No | TBD
10331 | Healthcare Personnel Safety, Dialysis | COVID-19 | A&R: Labels for Variables in ADS Summary Line List Reports | 3-Medium | A&R-In-Progress | 2022-07-27 18:07 | For the Dialysis component, the variables ‘pctPatAllVacc’ and ‘pctPatVaccNoDec’ do not have descriptive labels populate when modifying the summary line list report and using the ‘Show descriptive variable names’ option. The affected Analysis Data set is ‘Dial_COVID19_VaccSUM_Pat.’ For the HPS component, the variables ‘pctAnyCore’ and ‘vaccLoc’ do not have descriptive labels populate when modifying the summary line list report and using the ‘Show descriptive variable names’ option. The affected Analysis Data Set is ‘HCW_COVID19_VaccSum_HCP’. | No | TBD
10224 | Dialysis | Survey(s) | A&R_"numHepBVaccStaff variable is missing from the survey ADS" | 3-Medium | Open | 2022-05-10 15:07 | A view of the available variables in NHSN provided evidence that the numHepBVaccStaffJan and numHepBVaccStaffFeb are available, but there is no numHepBVaccStaff variable option. | No | TBD
10377 | Dialysis | Analysis and Reporting | June 2022 MRP not showing up on QIP Report - orgid 89879 | 2-High | Open | 2022-10-14 08:52 | When the facility selected the option Not Participating in NHSN on the Monthly Reporting Plan, the facility did not appear on the group QIP report. The facility should appear on the group QIP report whether or not the Not Participating in NHSN box is checked on the Monthly Reporting Plan. | Yes | TBD
10409 | Dialysis | Analysis and Reporting | NHSN LINE LISTING EVENT AND SIR MISSING VALUES | 2-High | Open | 2022-11-15 16:33 | Missing Values in the Events and SIR column, there should be values in both areas even if they are 0. | No | TBD